## Current
Operation | Duration | Dependency 1 | Dependency 2 | Dependency 3 | Dependency 4 | Dependency 5 | Dependency 6 | Location X | Location Y | Location X 2 | Location Y 2 | Delay
Parking | 1 | [10 empty] | 0
Chocks_Front | 0.5 | Parking | [5 empty] | 960 | 910 |  |  | 0
Chocks_Rear | 0.5 | Chocks_Front | [5 empty] | 880 | 550 | 1040 | 550 | 0
Connect_GPU | 0.5 | Chocks_Front | [9 empty] | 0
Connect_PCA | 1 | Connect_GPU | Chocks_Rear | [8 empty] | 0
Connect_LDL_Rear | 1 | Connect_GPU | Chocks_Rear | [8 empty] | 0
Connect_LDL_Front | 1 | Connect_GPU | Chocks_Rear | [8 empty] | 0
Technical_Inspection | 24 | Connect_GPU | Chocks_Rear | [8 empty] | 0
Water_Service | 3 | Connect_GPU | Chocks_Rear | [8 empty] | 0
Refuel_Prep | 7 | Connect_GPU | Chocks_Rear | [8 empty] | 0
Connect_Bridge | 1.5 | Chocks_Rear | [9 empty] | 0
Offload_Rear | 10 | Connect_LDL_Rear | [5 empty] | 900 | 320 |  |  | 0
Deboard | 7 | Connect_Bridge | [5 empty] | 1052 | 902 |  |  | 0
Offload_Front | 12 | Connect_LDL_Front | [5 empty] | 900 | 825 |  |  | 0
Cabin_Cleaning | 13 | Deboard | [5 empty] | 960 | 560 |  |  | 0
Catering_Front | 8 | Deboard | [9 empty] | 0
Catering_Rear | 8 | Deboard | [9 empty] | 0
Toilet_Service | 3 | Deboard | [9 empty] | 0
Refuel | 5 | Refuel_Prep | [9 empty] | 0
Load_Rear | 19 | Offload_Rear | [5 empty] | 900 | 320 |  |  | 0
Cabin_Prep | 3 | Catering_Front | Catering_Rear |  |  |  |  | 960 | 560 |  |  | 0
Load_Front | 19 | Offload_Front | [5 empty] | 900 | 825 |  |  | 0
Refuel_Finalising | 11 | Refuel | [9 empty] | 0
Boarding | 22 | Cabin_Prep | Refuel | Cabin_Cleaning |  |  |  | 1052 | 902 |  |  | 0
Flight_Closure | 3 | Boarding | [5 empty] | 960 | 560 |  |  | 0
Remove_GPU | 0.5 | Technical_Inspection | Water_Service | Refuel_Finalising | Boarding | Toilet_Service | [5 empty] | 0
Remove_PCA | 0.5 | Connect_PCA | Technical_Inspection | Water_Service | Refuel_Finalising | Boarding | Toilet_Service |  |  |  |  | 0
Attach_Tug | 0.5 | Remove_GPU | Remove_PCA | [8 empty] | 0
Remove_LDL_Rear | 1 | Load_Rear | [9 empty] | 0
Remove_LDL_Front | 1 | Load_Front | [9 empty] | 0
PDCS | 2 | Remove_LDL_Front | Remove_LDL_Rear | Attach_Tug | Flight_Closure |  |  | 960 | 970 |  |  | 0
Pushback | 4 | PDCS | [9 empty] | 0