## Current
Operation | Duration | Dependency 1 | Dependency 2 | Dependency 3 | Dependency 4 | Dependency 5 | Location X | Location Y | Location X 2 | Location Y 2 | Delay
Parking | 1 | [9 empty] | 0
Chocks_Front | 1 | Parking |  |  |  |  | 960 | 910 |  |  | 0
Chocks_Rear | 1 | Chocks_Front |  |  |  |  | 880 | 550 | 1040 | 550 | 0
Place_Cones | 1 | Chocks_Front |  |  |  |  | 550 | 450 | 1370 | 450 | 0
Connect_GPU | 1 | Chocks_Front | [8 empty] | 0
Connect_LDL_Rear | 2 | Place_Cones | Connect_GPU | Chocks_Rear | [6 empty] | 0
Connect_LDL_Front | 4 | Place_Cones | Connect_GPU | Chocks_Rear | [6 empty] | 0
Technical_Inspection | 34 | Place_Cones | Connect_GPU | Chocks_Rear | [6 empty] | 0
Water_Service | 5 | Place_Cones | Connect_GPU | Chocks_Rear |  |  | 950 | 300 |  |  | 0
Refuel_Prep | 14 | Place_Cones | Connect_GPU | Chocks_Rear | [6 empty] | 0
Connect_Bridge | 2 | Chocks_Rear | [8 empty] | 0
Offload_Rear | 13 | Connect_LDL_Rear |  |  |  |  | 900 | 320 |  |  | 0
Deboard | 7 | Connect_Bridge |  |  |  |  | 1052 | 902 |  |  | 0
Offload_Front | 16 | Connect_LDL_Front |  |  |  |  | 900 | 756 |  |  | 0
Cabin_Cleaning | 13 | Deboard |  |  |  |  | 960 | 560 |  |  | 0
Catering_Front | 10 | Deboard | [8 empty] | 0
Catering_Rear | 10 | Deboard | [8 empty] | 0
Toilet_Service | 5 | Deboard |  |  |  |  | 1380 | 180 |  |  | 0
Refuel | 6 | Refuel_Prep | [8 empty] | 0
Load_Rear | 30 | Offload_Rear |  |  |  |  | 900 | 320 |  |  | 0
Cabin_Prep | 3 | Catering_Front | Catering_Rear |  |  |  | 960 | 560 |  |  | 0
Load_Front | 25 | Offload_Front |  |  |  |  | 900 | 756 |  |  | 0
Refuel_Finalasing | 14 | Refuel | [8 empty] | 0
Boarding | 22 | Cabin_Prep | Refuel |  |  |  | 1052 | 902 |  |  | 0
Flight_Closure | 3 | Boarding |  |  |  |  | 960 | 560 |  |  | 0
Remove_GPU | 1 | Technical_Inspection | Water_Service | Refuel_Finalasing | Boarding | Toilet_Service | 960 | 910 |  |  | 0
Attatch_Tug | 1 | Remove_GPU | [8 empty] | 0
Remove_LDL_Rear | 2 | Load_Rear | [8 empty] | 0
Remove_LDL_Front | 2 | Load_Front | [8 empty] | 0
Remove_Cones | 1 | Attatch_Tug |  |  |  |  | 550 | 450 | 1370 | 450 | 0
Walkaround | 2 | Attatch_Tug | [8 empty] | 0
PDCS | 2 | Remove_LDL_Front | Remove_LDL_Rear | Remove_Cones | Walkaround | Flight_Closure | 960 | 970 |  |  | 0
Pushback | 5 | PDCS | [8 empty] | 0